## Sheet1
Checksheet for Job Creation - Estimator
TIMBERLINE ESTIMATING
Clean up estimate & set cost codes
Print WBS Field Spreadsheet
Print WBS Load List - Bill of Material
Uncheck Profit Allocatables
Export Estimate: Interface > Job Cost
Recheck Profit Allocatables
Order any & all Long Lead or Difficult-to-get Materials; stage in Shop
JOB STAMP |  |  |  | Fill out the Job Stamp and include with the following items
ADMIN |  | Binder/ Tab # | EST | Items Needed for Job Binder
SOP | NEEDED?
X |  | 1 | n/a | Job Hand Off
X |  | 2 | n/a | Safety
|  | 3 |  | Proposal: supply a copy without price
Proposal: all contact info listed for job
|  | 4 |  | WBS Field Spreadsheet - highlight cost code descriptions
Drawings, details, specs
Photos
Copy of notes from Owner
|  | 5 |  | Map of job location Note: if delegated to Admin & address different from Co on PRO write it here:
|  | 6 |  | Vendors & Subs - copy of pertinent paperwork without pricing
Work orders/actual work completed documentation required?
|  | 7 |  | WBS Load List
|  | 8 |  | Underground locate
Permits
X |  | 9 | n/a | Job Close Out
X |  | 10 | n/a | Vendor list w/phone numbers & Dump site locations
X |  |  | n/a | Timberline: Change estimate status to "Awarded to LLG"
X |  |  | n/a | Timberline: Make sure company/contact is in Address Book
X |  |  | n/a | Enter date processed, highlight row light,olive green & enter "A" in column A in Estimate Numbers file