## PAGE ONE w bars
L.L. GEANS CONSTRUCTION CO. TIME CARD
Job Number: | 6485 |  | Job Name:Werntz Conference Center | [6 empty] | Estimator: MG | FOREMAN:**
REMEMBER TO COMPLETE ALL BOXES INDICATED WITH ** |  |  |  | WEEK ENDING**__________________DATE**__________________DAY**_________________ |  |  | DATE** ____________ |  | DAY**______________ |  | WEATHER:**
| Est. Approv | [9 empty] | IF EMPLOYEE IS NOT AT WORK
| COST CODE | 150 | 312 | [7 empty] | RECORD NAME & REASON
| DESCP | Mob & Demob | Install walk & tie steel | [7 empty] | OP=Operator F=Foreman B=Base
SK=Skilled Labor Un = Unskilled Labor
[10 empty] | TOTAL | START | STOP | LUNCH
EMPLOYEE NAME | Work Class | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | TIME | TIME | Y OR N
** | ** | ** | [8 empty] | ** | ** | **
Total Hours Today
Accumulated Hours | [9 empty] | DAYS OFF REASON CODE:
Est Hrs to Complete |  | 9 | 8 | 60 | [5 empty] | DO = Day off (excused)
Units Installed Today | [9 empty] | WC = Worker's Comp
Accumulated Units | [9 empty] | NS = No Show (unexcused)
Expected Installed Units | [9 empty] | R = Rain (available)
Estimated Total Units | [9 empty] | LO = Laid Off
Unit Description | [9 empty] | S = (excused)
Estimated Prod Rate/HR | [9 empty] | WO = Worked with someone else(list foreman)
Actual Prod Rate/HR | [9 empty] | L= Late for Work (Put an L next to start time)
Variance

## PAGE ONE
L.L. GEANS CONSTRUCTION CO. TIME CARD
Job Number: | 7397 |  | Job Name: Peerless/Niles | [6 empty] | Estimator: MG | FOREMAN:**
REMEMBER TO COMPLETE ALL BOXES INDICATED WITH ** |  |  |  | WEEK ENDING**__________________DATE**__________________DAY**_________________ |  |  | DATE** ____________ |  | DAY**______________ |  | WEATHER:**
| Est. Approv | [9 empty] | IF EMPLOYEE IS NOT AT WORK
| COST CODE | 150 | 200 | 301 | 001 | 002 | 312 |  |  |  | RECORD NAME & REASON
| DESCP | Mob & Demob | Excavate | Install footings | Masonry block work | All carpentry work | Install floor slab |  |  |  | OP=Operator F=Foreman B=Base
SK=Skilled Labor Un = Unskilled Labor
[10 empty] | TOTAL | START | STOP | LUNCH
EMPLOYEE NAME | Work Class | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | TIME | TIME | Y OR N
** | ** | ** | [8 empty] | ** | ** | **
Total Hours Today
Accumulated Hours | [9 empty] | DAYS OFF REASON CODE:
Est Hrs to Complete |  | 25 | 16 | 9 | 100 | 60 | 16 |  |  | DO = Day off (excused)
Units Installed Today | [9 empty] | WC = Worker's Comp
Accumulated Units | [9 empty] | NS = No Show (unexcused)
Expected Installed Units | [9 empty] | R = Rain (available)
Estimated Total Units | [9 empty] | LO = Laid Off
Unit Description | [9 empty] | S = (excused)
Estimated Prod Rate/HR | [9 empty] | WO = Worked with someone else(list foreman)
Actual Prod Rate/HR | [9 empty] | L= Late for Work (Put an L next to start time)
Variance

## PAGE ONE FOR GREEN CARDS
L.L. GEANS CONSTRUCTION CO. TIME CARD
Job Number: |  |  | Job Name: | [5 empty] | Estimator: |  | FOREMAN:**
REMEMBER TO COMPLETE ALL BOXES INDICATED WITH ** |  |  |  | WEEK ENDING**__________________DATE**__________________DAY**_________________ |  |  | DATE** ____________ |  | DAY**______________ |  | WEATHER:**
| Est. Approv | [9 empty] | IF EMPLOYEE IS NOT AT WORK
| COST CODE | [9 empty] | RECORD NAME & REASON
| DESCP | [9 empty] | OP=Operator F=Foreman B=Base
SK=Skilled Labor Un = Unskilled Labor
[10 empty] | TOTAL | START | STOP | LUNCH
EMPLOYEE NAME | Work Class | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS | TIME | TIME | Y OR N
** | ** | ** | [8 empty] | ** | ** | **
Total Hours Today
Accumulated Hours | [9 empty] | DAYS OFF REASON CODE:
Est Hrs to Complete | [9 empty] | DO = Day off (excused)
Units Installed Today | [9 empty] | WC = Worker's Comp
Accumulated Units | [9 empty] | NS = No Show (unexcused)
Expected Installed Units | [9 empty] | R = Rain (available)
Estimated Total Units | [9 empty] | LO = Laid Off
Unit Description | [9 empty] | S = (excused)
Estimated Prod Rate/HR | [9 empty] | WO = Worked with someone else(list foreman)
Actual Prod Rate/HR | [9 empty] | L= Late for Work (Put an L next to start time)
Variance

## PAGE TWO
FOREMAN'S FIELD REPORT PAGE 2
MATERIAL RECEIVED SECTION | JOB NO. - COST CODE | TYPE | SOURCE | QUANTITY | RECEIVER
[5 empty] | YES | NO*
*IF NO, WHY NOT?
SUBS AND RENTAL EQUIPMENT SECTION | JOB NO. - COST CODE | SUBCONTRACTORS WORKING AND RENTAL EQUIPMENT |  | WORK PERFORMED |  | HOURS
WORK PERFORMED TODAY COMMENTS
Services Connected/Disconnected? NO □ YES □ If yes, explain: Change Orders Received/Implemented? NO □ YES □ If yes, explain:
WORK TO BE PERFORMED TOMORROW /COMMENTS
CONSTRUCT- IVE CRITICISM -POSITIVE FEEDBACK REGRDING YOUR MEN | EMPLOYEE NAME | EMPLOYEE INITIALS |  |  | FOLLOW UP W/LETTER | FOLLOW UP W/MEETING
ACCIDENTS INJURIES THEFTS UNUSUAL EVENTS SAFETY VIOLATIONS | Accident(s)___________Theft or Vandalism Today_________Unusual Events_________Safety Violations________Incident Reported to HR?________
If so - describe event and emergency procedure taken:
ADDITIONAL WORK PERFORMED ON CONTRACT |  |  | The following items were secured in your truck lockbox at the end of the day_______Initial
Please list additional work and materials used for any work |  |  | _____Compactor | _____Laser
completed that was not on the original proposal and needs |  |  | _____Cordless Drill | _____Bull Float
to be billed in addition to the contract amount: |  |  | _____Hammer Drill | _____Sawzall
|  |  | _____Concrete Saw and Diamond Blade | _____Mini Grinder
|  |  | _____Circular Saw | _____Toolbox Locked ___ Truck Locked
Notes:
Complete this section if an item is missing:
Initial here if no extras done on this date |  | ________ | Item missing____________________Job site or location last seen__________________Time last seen_____
ATTACH ALL PAPERWORK: PACKING LISTS, RECEIPTS, ETC. AND SEND PLACE IN BOX.
Mob & Demob