## PAGE 1-drop down (hidden)
L.L. Geans Construction Co. Time Card
Date: | Cost Codes with Description | 1-3010 Constr Engineering - Field | 1-7113 Mob/Demob Crew Trailer | 1-7114 Mob/Demob Roll Off | 1-7213 Construction Layout | 2-4120 Flatwork Removal | 3-4600 Form - Prep - Place Pits Trenches/Bases/ Steps & Stoops |  |  | Job Number : |  | 110416
Day: | [9 empty] | Job Name:
Wk Ending: | [9 empty] | Modineer - Press Base
Crew Leader: | [9 empty] | EST: | MG
Weather: | [9 empty] | Estimator Approval:_________
Employee Name | Emp # | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hours | Start Time | Stop Time | Lunch Y or N
[11 empty] | Time | Time | Y Or N
Units Installed Today | [9 empty] | If employee is not at work,
Production Unit of Measure | [9 empty] | record name and reason code.
REASON CODE for BEING ABSENT:
Please list additional work and materials used for any work completed that was not on the original proposal and needs to be billed in addition to the | [9 empty] | WC = Workers Comp |  | S = (excused)
contract amount: | [9 empty] | R = Rain (available) |  | NS = No Show (unexcused)
[10 empty] | DO = Day off (excused) |  | LO = Laid Off
WO = Worked with someone else (list foreman)
Change Orders Received/Implemented? NO □ YES □ If yes, explain: | [9 empty] | L = Late for Work (Put an L next to start time)
1-3000 General Conditions
1-3010 Constr Engineering - Field
1-7113 Mob/Demob Crew Trailer
1-7114 Mob/Demob Roll Off
1-7213 Construction Layout
2-4113 Selective Site Demolition
2-4114 Paving Removal
2-4115 Site Materials Misc
2-4116 Mass Concrete Removal
2-4117 Unsuitable Material Removal
2-4120 Flatwork Removal
2-4125 Curb Removal
3-0010 All Concrete Work
3-0190 Patching
3-2000 Reinforcing Rebar
3-3001 Misc Mt'l & Labor
3-3002 Misc Mt'l & Labor
3-3003 Misc Mt'l & Labor
3-3200 Rub Finish w/Concrete Finisher
3-3533 Stamped Concrete Finishing
3-4000 Form - Prep - Place Walls
3-4050 Form - Prep - Place Footing
3-4200 Form - Prep - Place Slab on Grade
3-4210 Form - Prep - Place Paving
3-4220 Form - Prep - Place Ext Flatwork
3-4230 Form - Prep - Place City Walks
3-4400 All Concrete
3-4500 Form - Prep - Place Structural Slabs
3-4600 Form - Prep - Place Pits Trenches/Bases/ Steps & Stoops
3-4700 Form - Prep - Place Misc
3-8110 Saw Cutting
31-2200 Topsoil & Seed
31-2316 All Excavation
31-2350 Trucking
32-1610 Standard Concrete Curbs
32-1613 Comb Conc Curb & Gutter Type A
32-1614 Comb Conc. Curb & Gutter
32-4000 Pipe Bollards
33-4100 Install Drain Tile & Topsoil
4-0200 Masonry Work
5-0100 Metals
5-1000 Install Railing
6-1000 Carpentry
7-0110 Moisture Protection

## PAGE 1-Prevail Wage (hidden)
L.L. Geans Construction Co. Time Card
PREVAILING WAGE JOB
Date: | Cost Codes with Description | 1-7113 | 1-7114 | 1-3010 | 3-4230 | 3-4700 |  |  | Job Number : |  | 10-0227
Day: |  | Mob & Demob Crew Trailer | Mob & Demob Roll-Off | Construct. Engineering - Field | ADA Ramps and Walk | Stamped Concrete |  |  | Job Name:
Wk Ending: | [8 empty] | K & M Machine / Paving
Crew Leader: | [8 empty] | EST: | Mike
Weather: | [8 empty] | Estimator Approval:_________
Employee Name | Emp # | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hours | Start Time | Stop Time | Lunch Y or N
|  | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  | Time | Time | Y Or N
Units Installed Today | [8 empty] | If employee is not at work,
Unit of Measure | [8 empty] | record name and reason.
DAYS OFF REASON CODE:
Please list additional work and materials used for any work completed that was not on the original proposal and needs to be billed in addition to the | [8 empty] | WC = Worker's Comp |  | DO = Day off (excused)
contract amount: | [8 empty] | R = Rain (available) |  | NS = No Show (unexcused)
[9 empty] | S = (excused) |  | LO = Laid Off
WO = Worked with someone else (list foreman)
Change Orders Received/Implemented? NO □ YES □ If yes, explain: | [8 empty] | L= Late for Work (Put an L next to start time)

## PAGE 1-Cost Codes blank (hidden)
L.L. Geans Construction Co. Time Card
Date: | Cost Codes with Description | 1-7113 | 3-0190 | [5 empty] | Job Number : |  | 10-0471
Day: |  | Crew Trailer Mob/De-mob | Patching | [5 empty] | Job Name:
Wk Ending: | [8 empty] | Dosmann Repairs
Crew Leader: | [8 empty] | EST: | NE
Weather: | [8 empty] | Estimator Approval:_________
Employee Name | Emp # | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hours | Start Time | Stop Time | Lunch Y or N
|  | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  | Time | Time | Y Or N
Garrett Allison
Units Installed Today | [8 empty] | If employee is not at work,
Unit of Measure | [8 empty] | record name and reason.
DAYS OFF REASON CODE:
Please list additional work and materials used for any work completed that was not on the original proposal and needs to be billed in addition to the | [8 empty] | WC = Worker's Comp |  | DO = Day off (excused)
contract amount: | [8 empty] | R = Rain (available) |  | NS = No Show (unexcused)
[9 empty] | S = (excused) |  | LO = Laid Off
WO = Worked with someone else (list foreman)
Change Orders Received/Implemented? NO □ YES □ If yes, explain: | [8 empty] | L= Late for Work (Put an L next to start time)

## old PAGE 2 (hidden)
CREW LEADER'S FIELD REPORT - page 2
MATERIAL RECEIVED, SUBS OR RENTAL EQUIPMENT USED
Job No. Cost Code | Type | Vendor name, sub name or rental equipment |  | Quantity | Receivers
[5 empty] | Yes | No*
WORK PERFORMED TODAY
Services Connected/Disconnected? No____ Yes____ If yes, explain:
OPPORTUNITIES FOR IMPROVEMENT
Was all work done today up to L.L. Geans standards? Yes_______ No_________ If no, please list issue and action plan for correction below.
CONSTRUCTIVE CRITICISM, POSITIVE FEEDBACK REGARDING YOUR MEN
Employee Name | Employee Initials |  |  |  | Follow up w/letter | Follow up w/meeting
MILEAGE
Employee Name | From / To |  |  | Round Trip Miles | Start Time | Stop Time
/
/
Describe any accidents, theft or vandalism,unusual events or safety violations that occurred today. |  |  | The following items were secured in your truck lockbox at the end of the day_______Initial
|  |  | _____Compactor | _____Laser
|  |  | _____Cordless Drill | _____Bull Float
|  |  | _____Hammer Drill | _____Sawzall
|  |  | _____Concrete Saw and Diamond Blade | _____Mini Grinder
|  |  | _____Circular Saw | _____Toolbox Locked ___ Truck Locked
|  |  | _____Dewalt Cordless Kit | _____Chipping Hammer
Complete this section if an item is missing:
Item missing____________________Job site or location last seen_______________Time last seen________
ATTACH ALL PAPERWORK: PACKING LISTS, RECEIPTS, ETC. AND PLACE IN OFFICE IN-BOX.
Mob & Demob

## PAGE 1-blank
L.L. Geans Construction Co. Time Card
Date: | Cost Codes with Description | [8 empty] | Job Number :
Day: | [9 empty] | Job Name:
Wk Ending:
Crew Leader: | [9 empty] | EST:
Weather: | Job KPI | [8 empty] | Estimator Approval:_________
Employee Name | Emp # | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hours | Start Time | Stop Time | Lunch Y or N
[11 empty] | Time | Time | Y Or N
Anticipated MH for today | [9 empty] | If employee is not at work, record name & reason code.
Units to Install today
KPI Goal for today | [9 empty] | REASON CODE for BEING ABSENT:
Actual MH for today | [9 empty] | WC = Workers Comp |  | S = (excused)
Actual Units Installed today | [9 empty] | R = Rain (available) |  | NS = No Show (unexcused)
KPI Actual for today | [9 empty] | DO = Day off (excused) |  | LO = Laid Off
KPI Variance = (KPI Actual - Job KPI) " + " exceeded KPI; " - " did not meet KPI | [9 empty] | WO = Worked with someone else (list foreman)
L = Late for Work (Put an L next to start time)
Please list additional work and materials used for any work completed that was not on the original proposal and needs to be billed in addition to the Contract Amount:
Change Orders Received/Implemented? NO □ YES □ If yes, explain:

## Page 1-RRG
L.L. Geans Construction Co. Time Card |  |  |  | COST CODES: 3-
Date: | Cost Codes with Description | 1-3010 Constr Engineering - Field | 1-7113 Mob/Demob Mt'l, Tools, Equip | [6 empty] | Job Number : |  | 120339
Day: | [9 empty] | Job Name:
Wk Ending: | [9 empty] | The Brick LLC - Curb
Crew Leader: | [9 empty] | EST: | RRG
Weather: | Job KPI | [8 empty] | Estimator Approval:_________
Employee Name | Emp # | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hours | Start Time | Stop Time | Lunch Y or N
[11 empty] | Time | Time | Y Or N
Anticipated MH for today | [9 empty] | If employee is not at work, record name & reason code.
Units to Install today
KPI Goal for today | [9 empty] | REASON CODE for BEING ABSENT:
Actual MH for today | [9 empty] | WC = Workers Comp |  | S = (excused)
Actual Units Installed today | [9 empty] | R = Rain (available) |  | NS = No Show (unexcused)
KPI Actual for today | [9 empty] | DO = Day off (excused) |  | LO = Laid Off
KPI Variance = (KPI Actual - Job KPI) " + " exceeded KPI; " - " did not meet KPI | [9 empty] | WO = Worked with someone else (list foreman)
L = Late for Work (Put an L next to start time)
Please list additional work and materials used for any work completed that was not on the original proposal and needs to be billed in addition to the Contract Amount:
Change Orders Received/Implemented? NO □ YES □ If yes, explain:
1-3000 General Conditions
1-3010 Constr Engineering - Field
1-4123 Dump Fees
1-5616 Temp Dust Barriers
1-7113 Mob/Demob Mt'l, Tools, Equip
1-7114 Mob/Demob Roll Off
1-7213 Construction Layout
2-4113 Selective Site Demolition
2-4114 Paving Removal
2-4115 Site Materials Misc
2-4116 Mass Concrete Removal
2-4117 Unsuitable Material Removal
2-4120 Flatwork Removal
2-4125 Curb Removal
3-0010 All Concrete Work
3-0190 Patching
3-0312 All work for Flatwork
3-2000 Reinforcing Rebar
3-3001 Misc Mt'l & Labor
3-3002 Misc Mt'l & Labor
3-3003 Misc Mt'l & Labor
3-3105 Setting Embedded Items
3-3200 Rub Finish w/Concrete Finisher
3-3533 Stamped Concrete Finishing
3-4000 Form - Prep - Place Walls
3-4050 Form - Prep - Place Footing
3-4070 Form - Prep - Place Pier/ Col Footings
3-4200 Form - Prep - Place Slab on Grade
3-4210 Form - Prep - Place Paving
3-4220 Form - Prep - Place Ext Flatwork
3-4230 Form - Prep - Place City Walks
3-4400 All Concrete
3-4500 Form - Prep - Place Structural Slabs
3-4600 Form - Prep - Place Pits Trenches/Bases/ Steps & Stoops
3-4700 Form - Prep - Place Misc
3-8100 Saw Cut Green Concrete
3-8110 Saw Cutting w/ Walk Behind
3-8120 Saw Cutting w/Handheld
3-8123 Concrete Core Drilling
31-2200 Topsoil & Seed
31-2316 All Excavation
31-2323 Backfill & Compaction
31-2350 Trucking
32-1610 Standard Concrete Curbs
32-1611 Concrete Curb Type C
32-1613 Comb Conc Curb & Gutter Type A
32-1614 Comb Conc. Curb & Gutter
32-1616 Curb & Gutter
32-2000 Columns, etc
32-4000 Pipe Bollards
33-4100 Install Drain Tile & Topsoil
4-0120 Unit Masonry Restoration
4-0200 Masonry Work
4-1000 Assist Masonry Sub
5-0100 Metals
5-1000 Install Railing
6-1000 Carpentry
7-0110 Moisture Protection

## Page 1- ASM
L.L. Geans Construction Co. Time Card |  |  |  | COST CODES: 3-0010 Install PVC Pipe 3-4220 Prep & Place Ext Flatwork 3-8120 Flatwork Removal 31-2316 Backfill, compact & prep for pour
Date: | Cost Codes with Description | 1-3010 Constr Engineering - Field | 1-7113 Mob/Demob Mt'l, Tools, Equip | [6 empty] | Job Number : |  | 130191
Day: | [9 empty] | Job Name:
Wk Ending: | [9 empty] | Koontz-Wagner - Drywell
Crew Leader: | [9 empty] | EST: | ASM
Weather: | Job KPI | [8 empty] | Estimator Approval:_________
Employee Name | Emp # | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hours | Start Time | Stop Time | Lunch Y or N
[11 empty] | Time | Time | Y Or N
Anticipated MH for today | [9 empty] | If employee is not at work, record name & reason code.
Units to Install today
KPI Goal for today | [9 empty] | REASON CODE for BEING ABSENT:
Actual MH for today | [9 empty] | WC = Workers Comp |  | S = (excused)
Actual Units Installed today | [9 empty] | R = Rain (available) |  | NS = No Show (unexcused)
KPI Actual for today | [9 empty] | DO = Day off (excused) |  | LO = Laid Off
KPI Variance = (KPI Actual - Job KPI) " + " exceeded KPI; " - " did not meet KPI | [9 empty] | WO = Worked with someone else (list foreman)
L = Late for Work (Put an L next to start time)
Please list additional work and materials used for any work completed that was not on the original proposal and needs to be billed in addition to the Contract Amount:
Change Orders Received/Implemented? NO □ YES □ If yes, explain:
1-3000 General Conditions
1-3010 Constr Engineering - Field
1-4123 Dump Fees
1-5616 Temp Dust Barriers
1-7113 Mob/Demob Mt'l, Tools, Equip
1-7114 Mob/Demob Roll Off
1-7213 Construction Layout
2-4113 Selective Site Demolition
2-4114 Paving Removal
2-4115 Site Materials Misc
2-4116 Mass Concrete Removal
2-4117 Unsuitable Material Removal
2-4120 Flatwork Removal
2-4125 Curb Removal
3-0010 All Concrete Work
3-0190 Patching
3-0312 All work for Flatwork
3-2000 Reinforcing Rebar
3-3001 Misc Mt'l & Labor
3-3002 Misc Mt'l & Labor
3-3003 Misc Mt'l & Labor
3-3105 Setting Embedded Items
3-3200 Rub Finish w/Concrete Finisher
3-3533 Stamped Concrete Finishing
3-4000 Form - Prep - Place Walls
3-4050 Form - Prep - Place Footing
3-4070 Form - Prep - Place Pier/ Col Footings
3-4200 Form - Prep - Place Slab on Grade
3-4210 Form - Prep - Place Paving
3-4220 Form - Prep - Place Ext Flatwork
3-4230 Form - Prep - Place City Walks
3-4400 All Concrete
3-4500 Form - Prep - Place Structural Slabs
3-4600 Form - Prep - Place Pits Trenches/Bases/ Steps & Stoops
3-4700 Form - Prep - Place Misc
3-8100 Saw Cut Green Concrete
3-8110 Saw Cutting w/ Walk Behind
3-8120 Saw Cutting w/Handheld
3-8123 Concrete Core Drilling
31-2200 Topsoil & Seed
31-2316 All Excavation
31-2323 Backfill & Compaction
31-2350 Trucking
32-1610 Standard Concrete Curbs
32-1611 Concrete Curb Type C
32-1613 Comb Conc Curb & Gutter Type A
32-1614 Comb Conc. Curb & Gutter
32-1616 Curb & Gutter
32-2000 Columns, etc
32-4000 Pipe Bollards
33-4100 Install Drain Tile & Topsoil
4-0120 Unit Masonry Restoration
4-0200 Masonry Work
4-1000 Assist Masonry Sub
5-0100 Metals
5-1000 Install Railing
6-1000 Carpentry
7-0110 Moisture Protection

## Page 1-CAP
L.L. Geans Construction Co. Time Card |  |  |  | COST CODES: 2-
Date: | Cost Codes with Description | 1-3010 Constr Engineering - Field | 1-7113 Mob/Demob Mt'l, Tools, Equip | [6 empty] | Job Number : |  | 130037
Day: | [9 empty] | Job Name:
Wk Ending: | [9 empty] | Woodcox - LaPorte Medical Group
Crew Leader: | [9 empty] | EST: | CAP
Weather: | Job KPI | [8 empty] | Estimator Approval:_________
Employee Name | Emp # | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Hours | Start Time | Stop Time | Lunch Y or N
[11 empty] | Time | Time | Y Or N
Anticipated MH for today | [9 empty] | If employee is not at work, record name & reason code.
Units to Install today
KPI Goal for today | [9 empty] | REASON CODE for BEING ABSENT:
Actual MH for today | [9 empty] | WC = Workers Comp |  | S = (excused)
Actual Units Installed today | [9 empty] | R = Rain (available) |  | NS = No Show (unexcused)
KPI Actual for today | [9 empty] | DO = Day off (excused) |  | LO = Laid Off
KPI Variance = (KPI Actual - Job KPI) " + " exceeded KPI; " - " did not meet KPI | [9 empty] | WO = Worked with someone else (list foreman)
L = Late for Work (Put an L next to start time)
Please list additional work and materials used for any work completed that was not on the original proposal and needs to be billed in addition to the Contract Amount:
Change Orders Received/Implemented? NO □ YES □ If yes, explain:
1-3000 General Conditions
1-3010 Constr Engineering - Field
1-4123 Dump Fees
1-5616 Temp Dust Barriers
1-7113 Mob/Demob Mt'l, Tools, Equip
1-7114 Mob/Demob Roll Off
1-7213 Construction Layout
2-4113 Selective Site Demolition
2-4114 Paving Removal
2-4115 Site Materials Misc
2-4116 Mass Concrete Removal
2-4117 Unsuitable Material Removal
2-4120 Flatwork Removal
2-4125 Curb Removal
3-0010 All Concrete Work
3-0190 Patching
3-0312 All work for Flatwork
3-2000 Reinforcing Rebar
3-3001 Misc Mt'l & Labor
3-3002 Misc Mt'l & Labor
3-3003 Misc Mt'l & Labor
3-3105 Setting Embedded Items
3-3200 Rub Finish w/Concrete Finisher
3-3533 Stamped Concrete Finishing
3-4000 Form - Prep - Place Walls
3-4050 Form - Prep - Place Footing
3-4070 Form - Prep - Place Pier/ Col Footings
3-4200 Form - Prep - Place Slab on Grade
3-4210 Form - Prep - Place Paving
3-4220 Form - Prep - Place Ext Flatwork
3-4230 Form - Prep - Place City Walks
3-4400 All Concrete
3-4500 Form - Prep - Place Structural Slabs
3-4600 Form - Prep - Place Pits Trenches/Bases/ Steps & Stoops
3-4700 Form - Prep - Place Misc
3-8100 Saw Cut Green Concrete
3-8110 Saw Cutting w/ Walk Behind
3-8120 Saw Cutting w/Handheld
3-8123 Concrete Core Drilling
31-2200 Topsoil & Seed
31-2316 All Excavation
31-2317 Excavation & Backfill
31-2323 Backfill & Compaction
31-2350 Trucking
32-1610 Standard Concrete Curbs
32-1611 Concrete Curb Type C
32-1613 Comb Conc Curb & Gutter Type A
32-1614 Comb Conc. Curb & Gutter
32-1616 Curb & Gutter
32-2000 Columns, etc
32-4000 Pipe Bollards
33-4100 Install Drain Tile & Topsoil
4-0120 Unit Masonry Restoration
4-0200 Masonry Work
4-1000 Assist Masonry Sub
5-0100 Metals
5-1000 Install Railing
6-1000 Carpentry
7-0110 Moisture Protection

## PAGE 2
CREW LEADER'S FIELD REPORT - page 2
DOCUMENT MISSING RECEIVERS FOR MATERIAL RECEIVED, SUBS, OR RENTAL EQUIPMENT USED
Job No. ¦ Cost Code | Type | Vendor name, Sub name or Rental equipment used |  |  |  | Quantity
WORK PERFORMED TODAY
Quality of Work: Was 1/4" in 10' rule met? Yes _____ No _____ If no, explain:
Services Connected/Disconnected? No______ Yes_____ If yes, explain:
OPPORTUNITIES FOR IMPROVEMENT
1. Were there any Accidents to an Employee (injury or illness)? |  |  | Yes_______ No_________ If yes, please complete Supervisor's Accident Report & attach.
2. Were there any Accidents to Property, Tools, &/or Equipment? |  |  | Yes_______ No_________ If yes, please complete Supervisor's Accident Report & attach.
3. Was all work done today up to L.L. Geans standards? Yes_______ No_________ If no, please list issue and action plan for correction below.
CONSTRUCTIVE CRITICISM, POSITIVE FEEDBACK REGARDING YOUR MEN
Employee Name | Employee Initials |  |  |  |  | Follow up w/letter | Follow up w/meeting
MILEAGE
Employee Name | From / To |  |  |  | Round Trip Miles | Start Mileage | Stop Mileage
/
Describe any accidents, theft or vandalism, unusual events or safety violations that occurred today. |  |  |  | The following items were secured in your truck lockbox at the end of the day_______Initial
|  |  |  | _____Compactor | _____Laser
|  |  |  | _____Cordless Drill | _____Bull Float
|  |  |  | _____Hammer Drill | _____Sawzall
|  |  |  | _____Concrete Saw and Diamond Blade | _____Mini Grinder
|  |  |  | _____Circular Saw | _____Toolbox Locked ___ Truck Locked
|  |  |  | _____Dewalt Cordless Kit | _____Chipping Hammer
Complete this section if an item is missing:
Item missing____________________Job site or location last seen_______________Time last seen________
ATTACH ALL PAPERWORK: PACKING LISTS, RECEIPTS, ETC. AND PLACE IN OFFICE IN-BOX.
]'[